THE GRAVITY SYSTEM

# Improvement
Implementation Kit

ASSESS • LAUNCH • MEASURE • COACH • VERIFY • SUSTAIN

The complete companion for the 30-Day Accelerated and 60-Day Guided plan libraries

Published by Thomas Monroe Books
Author and System Developer: Thomas Butler

# Welcome to the Gravity Improvement System

A practical system for turning operating concerns into measured, teachable, sustainable improvement.

Thank you for trusting The Gravity System. This kit was designed so a manager can begin with clarity, protect employees and guests during change, and finish with evidence—not assumptions. It supports every plan in both improvement libraries.

THE GRAVITY PROMISE Improvement must never come at the expense of food safety, hospitality, product quality, employee dignity, fairness, legal compliance, or a workload the team cannot sustain.

# What this kit helps you do

Choose the correct first plan instead of chasing the loudest complaint.

Establish trustworthy definitions and a representative baseline.

Explain the project without blaming or threatening employees.

Train, observe, coach, and document consistently.

Decide whether to standardize, extend, redesign, or stop the change.

Carry improvement forward after the calendar ends.

# Your first five actions

| Step | Action | Complete |
| --- | --- | --- |
| 1 | Choose the correct edition and improvement area. | ☐ |
| 2 | Name one accountable manager and supporting roles. | ☐ |
| 3 | Define the metric and collect the baseline before coaching. | ☐ |
| 4 | Explain the purpose and protections to employees. | ☐ |
| 5 | Start the selected calendar and document each checkpoint. | ☐ |

# Choose the Right Edition

| Edition | Best Fit | Use When |
| --- | --- | --- |
| 30-Day Accelerated | Established managers and disciplined teams | Reliable data exists; daily follow-through and compressed training are realistic. |
| 60-Day Guided | Beginning managers, newer teams, or lower implementation capacity | The team needs additional explanation, repetition, observation, coaching, and correction. |

SAME STANDARD Both editions use the same measures, operating protections, and intended outcomes. The 60-day edition is not a reduced standard; only pacing and implementation support differ.

# Do not run both versions of the same plan

Choose one edition based on current management capacity. Switching is appropriate only when documented conditions show that the chosen pace is unrealistic. Preserve completed evidence and restart from the equivalent phase—not automatically from Day 1.

# Capacity test

☐  A manager can protect daily ownership and documentation.

☐  Baseline data can be collected without changing employee behavior early.

☐  Required employees can be trained and observed within the selected pace.

☐  Scheduled reviews will occur even during demanding operating weeks.

☐  The operation can correct setbacks without abandoning the standard.

If three or more statements cannot be confirmed, begin with the 60-Day Guided edition.
Selected edition: ☐ 30-Day Accelerated   ☐ 60-Day Guided   Approved by: ____________________

# What Every File Is For

| File | Purpose | Open It When |
| --- | --- | --- |
| README FIRST | Explains package contents and recommended order. | Immediately after extraction. |
| START HERE | Introduces the library, sequence, and rules. | Before selecting a plan. |
| Complete Master PDF | Contains all 12 plans in one printable reference. | For management review or complete printing. |
| Editable Word Master | Allows local notes and approved customization. | When preparing an internal working copy. |
| Individual Plan PDFs | Provides one clean plan without unrelated material. | When launching a selected plan. |
| Implementation Kit | Provides assessment, training, measurement, forms, glossary, and support. | Before and throughout implementation. |
| Printable Forms | Provides clean reusable records. | When more than one copy is needed. |
| Expansion Roadmap | Shows future improvement categories. | After the Priority 12 are stable. |

# Improvement-Area Assessment

Score observed operating evidence—not personalities. Use 0 if no concern is present and 4 if the concern is frequent, costly, or damaging.

| Improvement Area | Evidence to Consider | Score 0–4 |
| --- | --- | --- |
| Customer Order Pacing | Courses collide, long gaps occur, or guests feel rushed. | ___ |
| Table-Turn Time | Preventable delays exist in payment, pre-bussing, resetting, or table release. | ___ |
| Kitchen Ticket-Time Consistency | Ticket times vary widely or peak-period production becomes unpredictable. | ___ |
| Order Accuracy and Remakes | Incorrect items, missed modifications, or avoidable remakes occur. | ___ |
| Labor-Hours Forecasting | Scheduled hours do not reliably match expected demand and workload. | ___ |
| Shift Deployment | The right number of people may be present but positioned poorly. | ___ |
| Station and Pre-Shift Readiness | Shifts begin without verified pars, tools, product, or assignments. | ___ |
| Average Guest Check | Appropriate recommendations and add-ons are inconsistent. | ___ |
| Guest Complaint Recovery | Complaints are handled inconsistently or learning is not documented. | ___ |
| Food-Waste Reduction | Waste, spoilage, overproduction, or portion variance lacks control. | ___ |
| Training Completion and Task Mastery | Completion is mistaken for demonstrated competence. | ___ |
| Daily Sales and Operating-Factor Review | Sales, weather, events, calendar effects, and labor needs are not connected. | ___ |

Highest score: ____________________   Evidence verified by: ____________________   Date: __________

# Plan-Selection Decision Record

| Decision Factor | Finding |
| --- | --- |
| Highest assessment score |  |
| Estimated financial or guest impact |  |
| Food-safety or legal urgency |  |
| Quality and hospitality risk |  |
| Management capacity |  |
| Data currently available |  |
| Recommended edition | ☐ 30-Day Accelerated ☐ 60-Day Guided |
| Selected plan |  |

# Selection rules

☐  Address immediate safety, legal, or severe guest harm before ordinary improvement work.

☐  Verify that the highest score reflects representative evidence rather than one unusual shift.

☐  Choose the plan with the strongest combination of urgency, controllability, and management capacity.

☐  Name one accountable owner before announcing the project.

☐  Record why another high-scoring plan was deferred.

Deferred priority and reason: ____________________________________________________________________________________
________________________________________________________________________________________________________________

# Launch authorization

| Required Approval | Name / Signature | Date |
| --- | --- | --- |
| Accountable manager |  |  |
| General manager / owner |  |  |
| Data or reporting owner |  |  |

READY TO BEGIN Launch only after the measure, baseline period, protections, ownership, and employee explanation are prepared.

# Manager Launch Checklist

# Before announcement

☐  Select the plan and edition using evidence.

☐  Define each measure, start point, stop point, exclusions, and data owner.

☐  Choose representative baseline dates and dayparts.

☐  Name the accountable manager and supporting roles.

☐  Confirm the project protects safety, quality, hospitality, fairness, and workload.

☐  Prepare forms, tools, training materials, and approved targets.

# Before Day 1

☐  Explain the purpose to employees without blame.

☐  State what will and will not be measured.

☐  Explain how unusual circumstances and exceptions will be recorded.

☐  Confirm managers will coach privately and consistently.

☐  Schedule required observations and review meetings.

☐  Record the official start and end dates.

# During and after

☐  Complete daily actions in order.

☐  Record coaching, exceptions, and evidence.

☐  Hold every scheduled review.

☐  Complete final verification.

☐  Document the sustained standard and ongoing owner.

# Employee Project Explanation

A plain-language manager script that can be adapted without changing its protections.

SAY THIS We are working on [improvement area] because we want the operation to be more consistent for guests and easier for the team to execute. This is not an attempt to blame employees for every delay or mistake. We will measure the full process, including staffing, tools, communication, workload, leadership decisions, and unusual circumstances. You will be shown the standard, given an opportunity to practice, and coached fairly. Please tell us when the process or tools make the standard difficult to achieve.

# Manager commitments

☐  We will explain the measure and standard before holding anyone accountable to it.

☐  We will separate system causes from individual performance.

☐  We will record unusual circumstances and legitimate exceptions.

☐  We will coach privately and recognize improvement publicly when appropriate.

☐  We will not trade safety, quality, hospitality, or dignity for a better number.

# Employee questions and concerns

| Question or Concern | Response / Follow-Up Owner | Due |
| --- | --- | --- |

# Measurement Guide: Build Trustworthy Evidence

# Define before measuring

| Element | Required Definition |
| --- | --- |
| Measure | Exactly what will be counted or timed. |
| Start point | The observable event that starts the measurement. |
| Stop point | The observable event that ends it. |
| Unit | Minutes, dollars, count, percentage, rate, or another stated unit. |
| Population | Which shifts, checks, tables, tickets, employees, or items are included. |
| Exclusions | Conditions excluded in advance and the reason. |
| Data owner | Who records, checks, and reports the information. |
| Review rhythm | When results are reviewed and by whom. |

# Representative baseline rules

Use enough observations to reflect normal variation; never select only the best or worst moments.

Include relevant dayparts, weekdays, weekends, volume levels, and event conditions.

Record weather, holidays, school schedules, local events, outages, staffing gaps, equipment problems, promotions, and other known operating factors.

Do not coach the targeted behavior until the baseline is complete unless immediate safety or legal risk requires action.

# Measurement Guide: Calculations and Interpretation

| Term | How to Calculate or Use It | Restaurant Example |
| --- | --- | --- |
| Rate | Events ÷ opportunities × 100 | 4 remakes ÷ 160 entrées × 100 = 2.5% remake rate. |
| Average | Sum of values ÷ number of values | Total ticket minutes ÷ tickets measured. |
| Median | Middle value after sorting | Useful when a few extreme tickets distort the average. |
| Percentage change | (New − baseline) ÷ baseline × 100 | Waste falls from $400 to $320: −20%. |
| Forecast variance | Actual − forecast; also show percentage | Actual sales $12,000 vs. $11,500 forecast: +$500 or +4.35%. |
| Outlier | A value materially outside the normal pattern | A 70-minute ticket during an equipment failure; record, explain, and review separately. |

INTERPRET CAREFULLY A better number does not prove a better operation. Check whether quality, safety, hospitality, employee workload, or another metric worsened at the same time.

# Minimum evidence standard

☐  Definitions stayed consistent.

☐  Baseline and current periods are comparable.

☐  Exceptions were documented rather than erased.

☐  Results are shown by relevant shift, daypart, volume, or category.

☐  The conclusion matches the evidence available.

# Completed Example: Customer Order Pacing

Illustrative example only. Each restaurant must establish its own baseline and approved target.

| Control | Completed Example |
| --- | --- |
| Plan owner | Jordan Lee, Assistant Manager |
| Dates | March 2–31 |
| Baseline period | February 16–22; dinner shifts |
| Primary area | Friday and Saturday dinner; Sections B and C |
| Supporting roles | FOH manager, expo, lead server, kitchen manager |

| Measure | Baseline | Target | Final |
| --- | --- | --- | --- |
| Median seating-to-greeting | 3.8 min | ≤ 2.5 min | 2.3 min |
| Median beverage-to-order entry | 11.2 min | ≤ 9.0 min | 8.7 min |
| Course-collision incidents | 14 per week | ≤ 9 per week | 8 per week |
| Pacing complaints | 5 per month | No increase | 2 per month |

# What the baseline showed

Servers batched greetings after simultaneous seating waves.

Orders were sometimes held without an approved pacing reason.

Expo and servers lacked a consistent course-readiness call.

Saturday weather and a nearby event increased walk-in volume beyond forecast.

# Completed Example: Decisions and Sustainment

| Checkpoint | Evidence | Decision |
| --- | --- | --- |
| Day 5 | Baseline confirmed across 42 complete table paths. | Proceed with standard design. |
| Day 10 | Definitions, responsibilities, and observation form approved. | Train two pilot sections. |
| Day 15 | Pilot improved greeting time; expo handoff still inconsistent. | Coach handoff and expand gradually. |
| Day 23 | Targets met on normal volume; one peak-period breakdown. | Stress-test Saturday peak. |
| Day 27 | Peak test passed after host–manager seating call. | Prepare sustained standard. |
| Day 30 | Primary metrics improved without quality or complaint harm. | Standardize and review weekly for four weeks. |

# Documented sustained method

Host alerts the floor manager before seating a third table into one section within five minutes.

Servers acknowledge newly seated tables immediately and follow the approved greeting standard.

Expo uses the course-readiness call before firing held entrées.

Manager reviews pacing exceptions each Monday and completes a monthly timed table-path audit.

WHY THIS EXAMPLE PASSES The conclusion uses comparable evidence, identifies system and staffing causes, records an event-related factor, verifies protections, and assigns continued ownership.

# Master Progress Dashboard

| Plan | Edition | Owner | Start | Target End | Status |
| --- | --- | --- | --- | --- | --- |
| Customer Order Pacing |  |  |  |  |  |
| Table-Turn Time |  |  |  |  |  |
| Kitchen Ticket-Time Consistency |  |  |  |  |  |
| Order Accuracy and Remakes |  |  |  |  |  |
| Labor-Hours Forecasting |  |  |  |  |  |
| Shift Deployment |  |  |  |  |  |
| Station and Pre-Shift Readiness |  |  |  |  |  |
| Average Guest Check |  |  |  |  |  |
| Guest Complaint Recovery |  |  |  |  |  |
| Food-Waste Reduction |  |  |  |  |  |
| Training Completion and Task Mastery |  |  |  |  |  |
| Daily Sales and Operating-Factor Review |  |  |  |  |  |

# Status definitions

| Status | Meaning |
| --- | --- |
| Not Started | No baseline work has begun. |
| Baseline | Definitions and representative evidence are being established. |
| Training | Standard is defined and employees are learning or practicing. |
| Active | Controlled execution, observation, and coaching are underway. |
| Verification | Results and protections are being confirmed. |
| Sustained | Improved method is documented with an ongoing owner and review rhythm. |
| Stopped / Redesigned | Evidence did not support continuation in the current form. |

# Weekly Review Record

| Project Information | Entry |
| --- | --- |
| Plan |  |
| Edition | ☐ 30-Day ☐ 60-Day |
| Owner |  |
| Review date |  |
| Days covered |  |
| Primary measure |  |

| Result | Primary Cause | Decision | Owner | Due |
| --- | --- | --- | --- | --- |

# Required review questions

☐  Did definitions or data collection change?

☐  What evidence improved, remained unchanged, or worsened?

☐  What unusual operating factors affected the period?

☐  Did another metric or protection deteriorate?

☐  What one action must be completed before the next review?

# Coaching and Observation Record

| Project Information | Entry |
| --- | --- |
| Plan / Standard |  |
| Employee or role observed |  |
| Observer |  |
| Date / shift |  |
| Operating conditions |  |

| Observed Behavior or Condition | Expected Standard | Coaching / Support Given | Follow-Up |
| --- | --- | --- | --- |

# Fair-coaching verification

☐  The standard had already been explained and practiced.

☐  Tools, staffing, workload, and system barriers were considered.

☐  Feedback described observable behavior rather than character.

☐  The employee had an opportunity to ask questions and try again.

☐  Follow-up evidence and ownership were documented.

# Troubleshooting Guide

| Problem | Check First | Corrective Response |
| --- | --- | --- |
| Employees resist the change | Were purpose, protections, and employee input explained? | Re-launch the explanation; address valid barriers; coach observable behavior privately. |
| Data is incomplete | Are definitions, tools, observation times, and ownership clear? | Pause conclusions; repair collection; extend the baseline or test. |
| Results initially worsen | Is this a learning effect, capacity problem, or genuine harm? | Reduce scope, retrain, and use a controlled pilot; stop if protections are threatened. |
| Managers stop following through | Is one owner accountable and are reviews scheduled? | Reset ownership, due dates, and visible review rhythm. |
| Target appears unrealistic | Was it based on baseline evidence and operating constraints? | Adjust only with documented evidence and approval—not to hide weak execution. |
| One shift improves and another does not | What differs in volume, staffing, leadership, mix, or conditions? | Segment the evidence and correct the specific constraint. |
| Speed improves but quality declines | Was a boundary metric omitted? | Reverse the harmful method and redesign with quality protection. |
| An event distorts results | Was it documented and is it likely to recur? | Report both ordinary and event-affected results; retain the event for future forecasting. |

# Final Verification and Sustainment Record

| Project Information | Entry |
| --- | --- |
| Plan |  |
| Edition | ☐ 30-Day ☐ 60-Day |
| Owner |  |
| Start / end |  |
| Primary measure |  |
| Baseline / final |  |

☐  Measurement definitions remained consistent.

☐  The baseline was representative and trustworthy.

☐  The standard was documented, trained, practiced, and observed.

☐  The primary result improved or the final decision explains why it did not.

☐  Safety, quality, hospitality, fairness, legal compliance, and workload were protected.

☐  Exceptions and operating factors were recorded.

☐  The ongoing owner and review rhythm are documented.

# Final decision

☐ Standardize   ☐ Extend controlled test   ☐ Redesign   ☐ Stop

Evidence supporting decision: __________________________________________________________________________________
________________________________________________________________________________________________________________

Ongoing owner: ____________________   Review rhythm: ____________________   Next review: __________

# Certificate of Verified Improvement

THE GRAVITY SYSTEM

VERIFIED IMPROVEMENT

This record confirms that

Restaurant / Location:  ____________________________________________

Improvement Plan:  ____________________________________________

Accountable Manager:  ____________________________________________

Implementation Dates:  ____________________________________________

Verified Result:  ____________________________________________

completed the Gravity measurement–standard–training–execution–verification process and documented continued ownership of the improved method.

Manager Signature: ____________________    Date: __________
Owner / GM Verification: ____________________    Date: __________

# Gravity Terms Glossary

Use these definitions consistently across both plan libraries.

| Term | Plain-Language Definition |
| --- | --- |
| Accountable manager | The one manager answerable for completion, evidence, decisions, and follow-through; supporting roles do not divide this accountability. |
| Actual | The verified result recorded after implementation for comparison with baseline and target. |
| Average | The sum of values divided by the number of values; useful but vulnerable to distortion by extreme results. |
| Baseline | The documented starting condition measured before targeted coaching or process change begins. |
| Boundary metric | A measure used to ensure improvement in one area does not damage safety, quality, hospitality, fairness, or workload. |
| Cause | A condition supported by evidence that contributes to a result; it should be tested rather than assumed. |
| Constraint | The factor currently limiting performance or capacity. |
| Controllable cause | A cause the restaurant can reasonably influence through decisions, tools, staffing, training, design, or execution. |
| Controlled pilot | A limited test with defined scope, ownership, measures, protections, and review conditions. |
| Course collision | Courses arriving too close together for the guest or operation to manage comfortably. |
| Daypart | A defined operating period such as breakfast, lunch, dinner, late night, or another locally meaningful period. |

# Gravity Terms Glossary — Continued

Use these definitions consistently across both plan libraries.

| Term | Plain-Language Definition |
| --- | --- |
| Deployment | Where and when available employees are positioned and what responsibilities they hold during the shift. |
| Exception | A documented circumstance handled outside the ordinary standard for a legitimate stated reason. |
| Forecast | A documented estimate of future sales, volume, demand, workload, or labor need using available evidence. |
| Forecast accuracy | How closely a forecast matches the actual result, normally expressed as an amount and percentage variance. |
| Governing factor | A condition such as weather, events, school schedules, holidays, construction, outages, or promotions that materially influences operations. |
| Handoff | The transfer of information, responsibility, product, or status from one person or station to another. |
| Hospitality boundary | The requirement that operational improvement must preserve respectful, attentive, guest-centered treatment. |
| Labor percentage | Labor cost divided by sales and multiplied by 100; definitions must state which labor costs and sales are included. |
| Median | The middle value after observations are sorted; often more representative when extreme values distort an average. |
| Metric | A specifically defined measure used to understand performance and change. |
| Observation | A documented review of actual conditions or behavior without relying only on opinion or memory. |

# Gravity Terms Glossary — Continued

Use these definitions consistently across both plan libraries.

| Term | Plain-Language Definition |
| --- | --- |
| Operating factor | Any internal or external condition that helps explain a result, including volume, staffing, menu mix, equipment, weather, or events. |
| Outlier | An observation materially outside the normal pattern that should be investigated and explained, not automatically erased. |
| Owner | The person assigned responsibility for an action or result; in a plan this may mean task owner, not restaurant proprietor. |
| Pilot | A limited implementation used to learn before expanding the standard. |
| Primary measure | The main metric used to evaluate whether the plan achieved its intended operating result. |
| Rate | The number of events divided by the number of opportunities, normally multiplied by 100. |
| Representative sample | Observations that reasonably reflect the shifts, volume, days, categories, and conditions relevant to the decision. |
| Remake rate | Remade items divided by applicable items produced, multiplied by 100, using a stated definition of remake. |
| Sales per labor hour | Net sales divided by labor hours worked for the defined period. |
| Standard | The documented, trainable, observable method or result expected under stated conditions. |
| Stress test | A controlled attempt to verify that the process can hold under demanding but relevant operating conditions. |

# Gravity Terms Glossary — Continued

Use these definitions consistently across both plan libraries.

| Term | Plain-Language Definition |
| --- | --- |
| Sustainment | The ownership, review rhythm, documentation, and corrective response used to prevent improvement from disappearing. |
| Table-turn time | The defined time from the selected occupancy start point through the selected departure or reset-ready endpoint; definitions must be consistent. |
| Target | The approved intended result, established from evidence and operating boundaries rather than wishful thinking. |
| Ticket time | The defined time from an approved order event to an approved completion event; start and stop points must be stated. |
| Training completion | Evidence that required instruction and practice occurred; it is not the same as demonstrated mastery. |
| Variance | The difference between expected and actual results, shown as an amount and often a percentage. |
| Verification | The final evidence-based confirmation that measurement, training, execution, protections, results, and ownership satisfy the plan requirements. |
| Waste percentage | Defined waste cost or quantity divided by the applicable production, purchases, or sales base, multiplied by 100. |
| Year-to-date sales | Cumulative sales from the beginning of the current year through the selected date, used with comparable prior periods and operating factors. |

# Frequently Asked Questions

Can we run more than one plan?
Yes, only when trained management capacity can protect ownership, data, training, coaching, and review for every active plan.

What if we miss a day?
Complete the missed required action before moving forward when sequence matters. Document the delay; do not pretend the action occurred.

Can we change a target?
Yes, when evidence shows the original target is unsafe, unrealistic, poorly defined, or no longer relevant. Record who approved the change and why.

Can we edit the Word file?
Yes. Preserve the original definitions, protections, evidence requirements, and decision logic. Save a clean original copy.

What if the baseline is unreliable?
Do not draw conclusions. Correct the measure and extend or repeat baseline collection.

What if results do not improve?
Determine whether execution, training, tools, capacity, or the selected cause was wrong. Extend a controlled test, redesign, or stop.

Should every outlier be removed?
No. Investigate it. Report ordinary and exceptional conditions separately when that improves understanding.

When is a plan complete?
When the result and protections are verified, the method is documented, and ongoing ownership is assigned—not merely when the calendar ends.

Which edition is better?
Neither universally. The correct edition is the one the current team can execute with integrity.

Can this replace professional advice?
No. Restaurants remain responsible for applicable laws, regulations, food-safety requirements, employment practices, accounting, and professional advice.

# What Comes Next

# After completing one plan

☐  Confirm the sustained owner and review rhythm.

☐  Continue boundary metrics long enough to detect regression.

☐  Update the assessment using current evidence.

☐  Select the next constraint without abandoning the prior standard.

☐  Carry forward useful operating factors, lessons, and employee feedback.

# A disciplined improvement cycle

| Stage | Question |
| --- | --- |
| Assess | What verified condition matters most now? |
| Measure | What is happening, under which conditions, and how do we know? |
| Standardize | What should happen and what protections must hold? |
| Train | Can people explain and demonstrate the method? |
| Execute | Does it work during representative operations? |
| Verify | Did the result improve without hidden harm? |
| Sustain | Who keeps the standard alive and when is it reviewed again? |

FINAL PRINCIPLE The calendar creates momentum. Evidence creates confidence. A usable standard and continued ownership create lasting improvement.