THE GRAVITY SYSTEM

# 60-Day Guided Restaurant
Improvement Plan Library

PRIORITY 12 • BEGINNING-LEVEL EMAIL MEMBER EDITION

Twelve guided plans for measurable restaurant improvement

Customer pacing • Table turns • Ticket times • Order accuracy
Labor forecasting • Deployment • Readiness • Average check
Complaint recovery • Food waste • Training mastery • Sales intelligence

Published by Thomas Monroe Books
Author and System Developer: Thomas Butler

# How to Use This Library

This complete Priority 12 guided edition is provided as a free resource for members of the Gravity Restaurant Leadership email list. Members may receive implementation guidance, new restaurant-management resources, Gravity System news, and relevant product information by email. Email membership is free, and members may unsubscribe at any time.

This edition preserves the exact improvement areas, operating standards, measures, and intended outcomes of the accelerated 30-day edition. It spreads the work across sixty days so beginning managers and slower-paced operations have additional time to understand the measures, practice the standard, coach employees, correct setbacks, and verify that the result can be sustained.

Use one plan at a time unless the restaurant has enough trained management capacity to protect ownership, measurement, coaching, and follow-through in every active plan.

# Which edition should I use?

| Choose | Best Fit | Commitment |
| --- | --- | --- |
| 30-Day Accelerated | Established managers; reliable operating data; employees accustomed to structured training; capacity for daily follow-through. | Faster implementation with compressed practice and review. |
| 60-Day Guided | Beginning managers; newer or smaller teams; limited systems experience; operations that need more teaching, repetition, or coaching. | The same standards and intended outcomes with a steadier learning pace. |

Quality promise: The 60-day edition is not a reduced standard. Both editions use the same measures, operating requirements, protections, and intended outcomes. Only the pacing and level of implementation support differ.

# The required operating sequence

| Period | Purpose |
| --- | --- |
| Days 1–10 | Learn the measure, observe the current operation, and establish a trustworthy baseline. |
| Days 11–20 | Define the standard, ownership, tools, target, and employee explanation. |
| Days 21–30 | Train in small groups, practice, and run a limited pilot. |
| Days 31–46 | Expand execution gradually, observe, coach, and record. |
| Days 47–54 | Stress-test the process and correct weak handoffs without abandoning the standard. |
| Days 55–60 | Verify results, document the improved method, and establish sustainment. |

# Rules that apply to every plan

Never improve one number by damaging food safety, hospitality, product quality, employee dignity, or legal compliance.

Define every metric before measuring it. Use medians, rates, and outliers where averages can hide the truth.

Record the baseline before coaching changes behavior.

Assign one accountable manager and named supporting roles.

Use the additional time for learning, practice, observation, and correction—not delay.

Document exceptions and causes; do not treat every variance as employee failure.

At Day 60, either standardize the improved method, extend the controlled test, redesign it, or stop the change.

# Priority order and compatibility

| Wave | Plans | Reason |
| --- | --- | --- |
| Wave 1 | Readiness; Order Pacing; Ticket-Time Consistency; Order Accuracy | Stabilizes the guest and production path. |
| Wave 2 | Table Turns; Labor Forecasting; Shift Deployment | Matches capacity and staffing to demand. |
| Wave 3 | Average Check; Complaint Recovery; Food Waste | Improves revenue, retention, and cost control. |
| Wave 4 | Training Mastery; Daily Sales & Operating-Factor Review | Protects learning and strengthens future decisions. |

# Plan 1: Customer Order Pacing

60-DAY OUTCOME  Create a natural, controlled meal pace from greeting through payment without rushing the guest or overwhelming the kitchen.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Door/seating-to-greeting time | ________ | ________ | ________ |
| Greeting-to-first beverage time | ________ | ________ | ________ |
| Beverage-to-order-entry time | ________ | ________ | ________ |
| Appetizer-to-entrée interval | ________ | ________ | ________ |
| Entrée-clear-to-check-ready time | ________ | ________ | ________ |
| Guest pacing complaints | ________ | ________ | ________ |

Recommended target boundaries

90% of tables greeted within the approved standard

90% of orders entered within the approved service window

Reduce course-collision incidents by at least 30% from baseline

No increase in pacing-related guest complaints

# Likely causes to test—not assume

Servers batch several tables before entering orders

Courses are entered or fired without table-readiness checks

Kitchen capacity is not considered during large arrival waves

Food runners and servers do not communicate course status

# Minimum operating standard

Acknowledge immediately and greet within the restaurant standard

Enter drinks and courses according to defined pacing checkpoints

Use hold/fire controls only under approved procedures

Communicate delays before the guest must ask

# Training requirements

Table pacing checkpoints

POS course and hold/fire functions

Reading guest pace without stereotyping

Server–expo–kitchen communication

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Define each pacing interval and select observation periods |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Time 20 complete table experiences without coaching |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Separate delays by host, server, bar, kitchen, runner, guest, or payment |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Map arrival waves against order-entry waves |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Review baseline and set realistic targets |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Publish the pacing standard and manager observation form |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train greeting, beverage, appetizer, entrée, dessert, and payment checkpoints |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Practice POS entry, course sequencing, and approved hold/fire controls |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Assign manager monitoring positions for peak periods |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Run a controlled pilot in one section and record results |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Expand the standard to all sections |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Coach order holding, batching, and course-collision behavior |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Review bar and kitchen constraints affecting pacing |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Recognize strong pacing that also preserves hospitality |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare current intervals with baseline and correct the weakest handoff |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Stress-test the standard during the busiest period |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Review pacing by server, daypart, table size, and menu type |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Correct any speed gains that make guests feel rushed |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Complete final observations and calculate improvement |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Publish the sustained pacing standard and weekly review rule |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Review pacing exceptions weekly and repeat a timed table-path audit monthly.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 2: Table-Turn Time

60-DAY OUTCOME  Reduce preventable table occupancy delays while protecting hospitality, food quality, and the guest’s right to enjoy the meal.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Seated-to-departure time by table size | ________ | ________ | ________ |
| Departure-to-reset-ready time | ________ | ________ | ________ |
| Check-request-to-payment-complete time | ________ | ________ | ________ |
| Unoccupied clean-table minutes | ________ | ________ | ________ |
| Quoted-wait accuracy | ________ | ________ | ________ |
| Rush-related complaints | ________ | ________ | ________ |

Recommended target boundaries

Reduce median turn time by 8–12% where baseline shows preventable delay

Reset 90% of departed tables within the approved reset standard

Reduce check/payment delays by at least 25%

No increase in rushed-guest complaints

# Likely causes to test—not assume

Slow greeting or ordering

Long ticket times or poor course pacing

Late pre-bussing and check presentation

Payment-processing delays

Unclear bussing and table-release ownership

# Minimum operating standard

Measure turn time by table size and daypart—not one universal number

Pre-bus without interrupting the guest

Offer the check at an appropriate readiness signal

Reset, inspect, and release the table through one clear handoff

# Training requirements

Turn-time components

Pre-bussing and check readiness

Payment and checkout urgency

Busser–host table-release communication

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Define start, stop, and reset-ready timestamps |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Measure 30 table turns by table size and daypart |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Break total time into greeting, ordering, production, dining, payment, and reset |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Identify the two largest controllable delays |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Set segment targets without creating guest pressure |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Publish table-turn and reset standards |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train servers, bussers, hosts, and managers together |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Practice pre-bussing, payment readiness, and table-release calls |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Pilot a visible clean/dirty/reset/available table status |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Review wait-list effects during the pilot |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Expand the process to all shifts |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Observe ten complete turns per day |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Correct handoff failures between server, busser, and host |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Compare table sizes and avoid unfair server rankings |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Review guest feedback for signs of rushing |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Test during the highest-volume service |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Correct the slowest controllable segment |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Verify quoted waits improve with better release information |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Complete final comparison by table size and daypart |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock the reset standard and weekly turn-time report |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Review median and 90th-percentile turn times weekly by table size; investigate extremes rather than chasing one average.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 3: Kitchen Ticket-Time Consistency

60-DAY OUTCOME  Reduce unpredictable and extreme ticket times while maintaining recipe, temperature, presentation, and safety standards.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Median ticket time | ________ | ________ | ________ |
| 90th-percentile ticket time | ________ | ________ | ________ |
| Longest ticket by period | ________ | ________ | ________ |
| Tickets outside standard | ________ | ________ | ________ |
| Station completion spread | ________ | ________ | ________ |
| Remakes caused by timing | ________ | ________ | ________ |

Recommended target boundaries

Reduce tickets outside standard by at least 30%

Reduce 90th-percentile ticket time by at least 15%

Reduce station completion spread on multi-station tickets

No deterioration in food-quality or safety checks

# Likely causes to test—not assume

Incomplete station readiness

Unbalanced station workload

Poor call-backs and fire sequencing

Batch order entry from dining room

Late identification of long tickets

# Minimum operating standard

Standards vary by menu category and order complexity

Expo calls and stations acknowledge priorities

Long tickets are identified before exceeding the standard

Speed never overrides temperature, allergen, recipe, or safety controls

# Training requirements

Ticket reading and sequencing

Station call-backs

Expo control and escalation

Recovery from volume surges

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Export or record ticket times by item category and period |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Measure median, 90th percentile, and outliers—not average alone |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Observe station workload during three peak periods |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Identify readiness, equipment, staffing, menu, and communication causes |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Set category standards and escalation points |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Publish station and expo timing standards |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train call-backs, priorities, and long-ticket alerts |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Verify pars, backups, equipment, and mise en place |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Pilot a five-minute peak-period ticket review rhythm |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Debrief the pilot with cooks, expo, runners, and managers |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Apply the rhythm on every peak shift |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Track the first station delay on each outlier ticket |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Adjust deployment or prep for repeating bottlenecks |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Practice surge recovery and honest guest-delay communication |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare median and 90th-percentile performance |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Stress-test on the busiest forecasted shift |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Audit food quality alongside speed |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Correct menu items or processes producing repeated extremes |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Complete final data comparison and station review |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock standards, alerts, and weekly outlier analysis |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Review outlier tickets weekly by station and item; update pars and deployment when patterns change.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 4: Order Accuracy and Remake Reduction

60-DAY OUTCOME  Reduce errors by controlling the entire order path: guest communication, POS entry, kitchen interpretation, preparation, expo, and delivery.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Remakes per 100 entrées | ________ | ________ | ________ |
| POS-entry errors | ________ | ________ | ________ |
| Modification errors | ________ | ________ | ________ |
| Kitchen-preparation errors | ________ | ________ | ________ |
| Expo/runner delivery errors | ________ | ________ | ________ |
| Remake cost and recovery time | ________ | ________ | ________ |

Recommended target boundaries

Reduce remakes per 100 entrées by at least 30%

Achieve 100% documented cause classification

Reduce repeated modification errors

Recover every affected guest through the approved process

# Likely causes to test—not assume

Incomplete read-back

Unclear POS modifiers

Recipe or allergy ambiguity

Expo verification gaps

Wrong-table or seat-number delivery

# Minimum operating standard

Clarify and confirm unusual orders before leaving the table

Use approved POS modifiers and seat numbers

Kitchen acknowledges critical modifications

Expo verifies item, modification, table, and presentation before release

# Training requirements

Order confirmation language

POS modifier and seat use

Allergy escalation

Expo and food-runner verification

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Define remake and error categories |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Audit 30 recent remakes or begin a five-day log |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Trace each error to the first failed control |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Calculate remake frequency and estimated cost |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Select the three highest-frequency error patterns |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Repair modifier buttons, recipes, or communication instructions |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train order confirmation and critical-modifier procedures |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Train kitchen acknowledgment and expo verification |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Practice accurate food-running with table and seat numbers |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Pilot the error log and immediate coaching process |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Review every remake before shift end |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Coach the first failed control rather than blaming the last handler |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Post temporary reminders for the top error patterns |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Recognize accurate execution during high volume |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare errors per 100 entrées with baseline |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Audit critical modifications and allergy handling |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Verify repaired POS buttons and recipe references |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Complete final remake and cost comparison |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Document unresolved equipment or menu-design risks |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock the monthly accuracy review and ownership |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Review every remake daily and the top three error patterns weekly until they remain controlled for eight weeks.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 5: Labor-Hours Forecasting

60-DAY OUTCOME  Convert forecasted sales, guests, workload, events, and service standards into defensible labor-hour requirements.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Forecasted versus actual sales | ________ | ________ | ________ |
| Forecasted versus actual guests | ________ | ________ | ________ |
| Scheduled versus required hours | ________ | ________ | ________ |
| Actual sales per labor hour | ________ | ________ | ________ |
| Labor percentage | ________ | ________ | ________ |
| Coverage failures and excess-hour incidents | ________ | ________ | ________ |

Recommended target boundaries

Establish a written labor-demand model for every daypart

Reduce forecast-to-actual labor-hour error over the baseline

Keep service-critical positions protected

Document all major forecast adjustments and causes

# Likely causes to test—not assume

Scheduling from habit

Using sales alone without workload or guest count

Ignoring events, weather, school, and promotions

No separation of fixed and variable labor

No forecast-error review

# Minimum operating standard

Begin with historical comparable days

Adjust for events, weather, promotions, reservations, and known changes

Calculate fixed opening/closing work separately from volume-driven hours

Record forecast, decision, actual result, and lesson

# Training requirements

Comparable-day selection

Sales and guest forecasting

Fixed versus variable labor

Forecast error and bias

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Collect four to eight comparable weeks of sales, guests, and hours |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Separate opening, service, and closing hours |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Identify fixed tasks and volume-driven positions |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Record known events and operating factors |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Build the first daypart labor-demand baseline |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Define staffing floors and productivity ranges |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train managers to document forecast assumptions |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Create the next seven-day sales, guest, and labor forecast |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Compare schedule hours with calculated need |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Approve changes using service-risk checks |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Record actual results daily |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Calculate forecast error and direction of bias |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Adjust for weather, events, reservations, and local patterns |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Correct recurring overstaffing or understaffing periods |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Produce the second seven-day forecast using lessons learned |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Test the model through a full schedule cycle |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Review service results alongside labor results |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Document where sales-per-hour measures are misleading |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Finalize daypart ranges and adjustment rules |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Publish the weekly forecast and post-shift learning rhythm |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Forecast seven days ahead, update 48 and 24 hours ahead, and review error and bias every week.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 6: Shift Deployment

60-DAY OUTCOME  Place the right trained people in the right positions at the right times and redeploy deliberately as volume changes.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Position coverage by 15/30-minute interval | ________ | ________ | ________ |
| Uncovered critical tasks | ________ | ________ | ________ |
| Manager interventions | ________ | ________ | ________ |
| Service bottlenecks | ________ | ________ | ________ |
| Early-cut reversals | ________ | ________ | ________ |
| Cross-trained coverage percentage | ________ | ________ | ________ |

Recommended target boundaries

100% named ownership for critical positions and transitions

Reduce unmanaged coverage gaps by at least 50%

Reduce unnecessary early-cut reversals

Document deployment changes during peak periods

# Likely causes to test—not assume

Managers treat the schedule as the deployment plan

No arrival-wave or cut sequence

Skills are not considered

Managers react after bottlenecks appear

Breaks and transitions are unmanaged

# Minimum operating standard

Publish opening, build, peak, decline, and closing positions

Name the trigger for adding, moving, or cutting labor

Protect critical stations and guest handoffs

Manager owns every deployment change

# Training requirements

Deployment maps

Volume triggers

Cross-position handoffs

Cuts, breaks, and recovery deployment

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Map required positions by daypart and volume band |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Observe three shifts and record coverage changes |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Identify critical positions and single points of failure |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Create a skills and cross-training matrix |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Draft opening, peak, decline, and closing deployment maps |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Train managers on deployment triggers and handoffs |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Brief employees on movement expectations |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Pilot maps on two representative shifts |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Record every unplanned move and the reason |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Revise triggers and cut sequence from pilot evidence |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Use deployment maps on all shifts |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Conduct scheduled manager scans before expected waves |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Coach delayed or unclear redeployment |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Protect breaks and handoffs |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare bottlenecks and intervention count with baseline |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Stress-test the peak deployment map |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Test one call-out contingency |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Finalize role cards and cross-training priorities |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Complete final coverage and service review |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock pre-shift deployment approval and post-shift variance notes |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Approve the deployment map before each shift and record every significant variance in the manager log.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 7: Station and Pre-Shift Readiness

60-DAY OUTCOME  Ensure every service-critical station, supply, employee, system, and contingency is ready before demand arrives.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Readiness checklist completion | ________ | ________ | ________ |
| Critical items missing at opening | ________ | ________ | ________ |
| Mid-shift stockouts | ________ | ________ | ________ |
| Equipment failures found after opening | ________ | ________ | ________ |
| Late prep tasks | ________ | ________ | ________ |
| Preventable service interruptions | ________ | ________ | ________ |

Recommended target boundaries

100% of critical readiness items verified, corrected, or escalated before service

Reduce preventable mid-shift interruptions by at least 40%

Zero unassigned critical readiness items

Document and correct every failed readiness check

# Likely causes to test—not assume

Checklist completion without physical verification

Unclear ownership

Par levels do not match forecasts

Equipment is not tested

Managers begin service without a readiness decision

# Minimum operating standard

Check, physically verify, correct, and sign—not merely initial

Use forecast-adjusted pars

Test critical equipment and POS functions

Manager declares ready, conditional, or not ready before service

# Training requirements

Station readiness standards

Forecast-adjusted pars

Equipment checks

Manager readiness decision

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | List every service-critical readiness condition |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Observe three openings and record failures discovered after service begins |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Separate station, staffing, equipment, product, facility, and information gaps |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Assign ownership and verification authority |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Set readiness deadlines by daypart |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Build concise station and manager checklists |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train physical verification and exception reporting |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Pilot forecast-adjusted pars and backup locations |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Run a formal readiness walk |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Revise items that are vague, duplicated, or unactionable |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Use the process every shift |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Track late corrections and mid-shift interruptions |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Coach false sign-offs immediately |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Review recurring equipment and purchasing issues |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare preventable interruptions with baseline |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Conduct an unannounced readiness audit |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Test one contingency for a missing product or failed tool |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Finalize escalation and conditional-opening rules |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Complete final readiness score |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock checklist ownership and weekly trend review |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Complete and verify readiness every shift; review recurring failures weekly and revise pars monthly.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 8: Average Guest Check

60-DAY OUTCOME  Increase average check through useful recommendations, menu knowledge, and complete hospitality—not pressure or manipulation.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Average check per guest | ________ | ________ | ________ |
| Appetizer attachment | ________ | ________ | ________ |
| Beverage attachment | ________ | ________ | ________ |
| Dessert attachment | ________ | ________ | ________ |
| Add-on attachment | ________ | ________ | ________ |
| Guest complaints about selling | ________ | ________ | ________ |

Recommended target boundaries

Increase average guest check 3–5% where capacity and concept support it

Improve at least two attachment categories

Achieve consistent recommendation observations

No increase in pressure-related complaints

# Likely causes to test—not assume

Weak menu knowledge

Generic scripted selling

Poor timing

Employees assume what guests can afford

No measurement by opportunity

# Minimum operating standard

Recommend only items that fit the guest’s stated preferences and occasion

Use specific descriptions and genuine choices

Offer at appropriate service checkpoints

Respect the first clear decline

# Training requirements

Menu knowledge and tasting

Preference questions

Specific recommendation language

Ethical sales boundaries

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Establish average check and attachment baselines |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Observe current recommendation behavior |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Identify high-value, high-satisfaction opportunities |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Review item availability and operational capacity |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Select two categories for the initial focus |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Train menu knowledge through taste, description, and pairing |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Practice preference-based questions and recommendations |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Define natural appetizer, beverage, add-on, and dessert moments |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Set observation—not quota—expectations |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Pilot with one meal period and review guest response |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Expand coaching to all servers |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Track attachment and average check by shift without public rankings |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Recognize helpful, accurate recommendations |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Correct robotic scripts and repeated pressure |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare sales lift with complaints, comps, and ticket time |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Refresh weak menu knowledge |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Review results by daypart and guest occasion |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Confirm kitchen and bar capacity remain protected |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Complete final check and attachment analysis |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock weekly coaching and monthly menu-opportunity review |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Review average check with guest satisfaction, attachment, comps, and ticket time so sales growth never damages hospitality.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 9: Guest Complaint Recovery

60-DAY OUTCOME  Resolve guest concerns quickly, respectfully, consistently, and in a way that produces organizational learning.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Complaints per 100 guests | ________ | ________ | ________ |
| Time to manager acknowledgment | ________ | ________ | ________ |
| Resolution at first contact | ________ | ________ | ________ |
| Repeat complaint themes | ________ | ________ | ________ |
| Follow-up completion | ________ | ________ | ________ |
| Guest return or response after recovery | ________ | ________ | ________ |

Recommended target boundaries

Manager acknowledgment within the approved standard

100% documentation of material complaints

100% assigned follow-up for unresolved causes

Reduce the leading repeated complaint category

# Likely causes to test—not assume

Employees become defensive

Managers arrive late

Authority limits are unclear

Recovery is not documented

The immediate guest is helped but the cause remains

# Minimum operating standard

Listen without interruption and acknowledge the effect

Clarify the desired resolution and act within authority

Never debate the guest at the table

Document the event, cause, recovery, owner, and follow-up

# Training requirements

Listen–acknowledge–resolve–verify

Manager escalation

Recovery authority

Cause classification and follow-up

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Review 30 days of complaints, comps, reviews, and manager notes |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Classify service, food, accuracy, speed, facility, policy, and expectation issues |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Measure response time and repeated themes |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Clarify employee and manager recovery authority |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Choose the leading repeat cause for correction |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Publish the recovery sequence and escalation triggers |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Train listening, acknowledgment, options, and verification |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Role-play common high-emotion situations |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Launch one complaint record and ownership log |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Pilot manager follow-up on material concerns |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Review every material complaint daily |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Coach defensive language and delayed escalation |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Correct the selected repeat cause operationally |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Verify promised follow-up occurs |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Compare resolution and recurrence with baseline |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Audit authority use, documentation, and privacy |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Review online and direct feedback together |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Complete final complaint-pattern analysis |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Recognize recoveries that protected dignity and learning |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock weekly complaint review and corrective-action ownership |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Review material complaints daily and patterns weekly; close the cause, not merely the conversation.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 10: Food-Waste Reduction

60-DAY OUTCOME  Reduce avoidable food loss without creating stockouts, unsafe reuse, undersized portions, or lower guest value.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Waste cost and weight | ________ | ________ | ________ |
| Waste by reason | ________ | ________ | ________ |
| Waste per $1,000 sales | ________ | ________ | ________ |
| Overproduction | ________ | ________ | ________ |
| Spoilage/expiration | ________ | ________ | ________ |
| Remake and returned-food waste | ________ | ________ | ________ |

Recommended target boundaries

Record at least 95% of material waste

Reduce the two leading controllable waste categories by 15–25%

Improve forecast-to-production alignment

No increase in stockouts or safety exceptions

# Likely causes to test—not assume

Waste is discarded without recording

Prep follows habit instead of forecast

Par levels are outdated

Portions and yields vary

Storage and rotation are weak

# Minimum operating standard

Record item, amount, reason, station, shift, and disposition

Never hide waste or reuse food unsafely

Use approved recipes, yields, portions, labels, and rotation

Adjust production from evidence, not blame

# Training requirements

Waste categories and honest reporting

Recipe, yield, and portion control

Forecast-based prep

Labeling, rotation, and safe disposition

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Define preparation, overproduction, spoilage, portion, remake, return, and transfer categories |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Weigh or count material waste for five days |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Convert waste to estimated cost |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Observe storage, rotation, prep, and portion practices |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Select the top two controllable categories |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Train simple, blame-free waste recording |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Verify recipes, yields, scoops, scales, and portions |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Adjust pars for forecast, shelf life, and delivery cycle |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Repair labeling and rotation gaps |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Pilot revised production on selected items |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Review waste at shift end |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Coach missing records and process causes |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Compare production, stockouts, and waste together |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Adjust one variable at a time |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Share verified savings and recognize honest reporting |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Audit portion and yield consistency |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Review vendor, receiving, and storage contributions |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Complete final waste-to-sales comparison |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Document safe pars and production rules |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock daily recording and weekly category review |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Record waste every shift, review causes weekly, and recalculate high-cost pars and yields monthly.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 11: Training Completion and Task Mastery

60-DAY OUTCOME  Replace “time spent training” with verified knowledge, demonstrated skill, consistent execution, and documented authorization.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Required modules completed | ________ | ________ | ________ |
| Knowledge checks passed | ________ | ________ | ________ |
| Observed demonstrations passed | ________ | ________ | ________ |
| Retraining frequency | ________ | ________ | ________ |
| Early errors by task | ________ | ________ | ________ |
| Trainer consistency | ________ | ________ | ________ |

Recommended target boundaries

100% assigned training has an owner and deadline

No independent assignment before required verification

At least 90% first-cycle completion by deadline

Reduce early task errors in the selected role

# Likely causes to test—not assume

Training is measured by days worked

Trainers teach different methods

Sign-offs are given without observation

Employees are assigned before readiness

Retraining is undocumented

# Minimum operating standard

Explain, demonstrate, practice, observe, verify, authorize

Use one approved method and standard

Sign-off means evidence was observed

Failed verification creates coaching and a new attempt—not punishment

# Training requirements

Trainer standardization

Demonstration and observation

Fair verification

Retraining and authorization

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Select one high-impact role or task family |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | List required knowledge, demonstrations, and safety gates |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Audit current completion and early error patterns |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Identify trainer differences |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Define evidence required for each sign-off |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Build or refine task verification records |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Calibrate trainers using the same demonstrations |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Train explain–demonstrate–practice–observe–verify |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Set authorization and retraining rules |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Pilot with one employee or task group |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Expand to the selected role |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Observe trainers as well as trainees |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Correct premature or unsupported sign-offs |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Track errors after authorization |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Hold brief progress reviews with trainees |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Recheck a sample of completed skills |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Compare early errors and retraining with baseline |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Document trainer and material gaps |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Finalize mastery and recertification rules |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock monthly training-file and field-performance audits |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Audit training records and observed field performance monthly; recertify safety- or control-critical skills on a defined schedule.

Manager verification: ____________________   Date: __________   Next review: __________

# Plan 12: Daily Sales and Operating-Factor Review

60-DAY OUTCOME  Create a searchable institutional memory connecting sales and labor results with weather, events, school schedules, promotions, traffic, and operating conditions.

| Control | Plan Requirement |
| --- | --- |
| Plan owner | ____________________________ |
| Start and end dates | ____________ to ____________ |
| Baseline period | ____________________________ |
| Primary shift/daypart | ____________________________ |
| Supporting roles | ____________________________ |

# Measures and targets

| Measure | Baseline | Day-60 Target | Actual |
| --- | --- | --- | --- |
| Daily records completed | ________ | ________ | ________ |
| Sales and guest variance versus forecast | ________ | ________ | ________ |
| YTD and comparable-day variance | ________ | ________ | ________ |
| Forecast error and bias | ________ | ________ | ________ |
| Event records captured | ________ | ________ | ________ |
| Labor-hour variance | ________ | ________ | ________ |

Recommended target boundaries

Complete 95% or more of daily records

Record every known material operating factor

Produce a weekly comparable-day learning summary

Use documented lessons in the next forecast and labor plan

# Likely causes to test—not assume

Sales are recorded without context

Event knowledge remains in one manager’s memory

Days cannot be searched by event or condition

Late-discovered factors cannot be added

Forecast accuracy is not measured

# Minimum operating standard

Record sales, guests, labor, weather, events, promotions, school dates, outages, and material conditions

Allow authorized later edits with date, editor, and reason

Tag recurring events consistently

Compare forecast, actual, variance, cause, and lesson

# Training requirements

Daily record completion

Event and factor tagging

Comparable-day search

Forecast error and bias

# The 60-Day Guided Action Calendar

| Day | Phase | Required Action |
| --- | --- | --- |
| 1 | Learn/Measure | Define required daily fields and controlled event tags |
| 2 | Learn/Measure | Review the completed step with the plan owner; clarify questions and document what was learned |
| 3 | Learn/Measure | Enter or import at least 14 prior comparable days |
| 4 | Learn/Measure | Repeat the step on a second representative shift or sample before accepting the result |
| 5 | Learn/Measure | Record weekday/weekend, weather, school, event, promotion, traffic, and operating notes |
| 6 | Learn/Measure | Explain the purpose to the affected employees and confirm understanding in plain language |
| 7 | Learn/Measure | Establish YTD and comparable-day calculations |
| 8 | Learn/Measure | Observe the process without taking over; record where additional instruction is needed |
| 9 | Learn/Measure | Set the daily completion deadline and owner |
| 10 | Learn/Measure | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 11 | Define/Prepare | Share baseline findings with managers and confirm no coaching began early |
| 12 | Define/Prepare | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 13 | Define/Prepare | Approve the target, definitions, and data owner |
| 14 | Define/Prepare | Review the completed step with the plan owner; clarify questions and document what was learned |
| 15 | Define/Prepare | Train managers on objective notes and consistent tags |
| 16 | Define/Prepare | Repeat the step on a second representative shift or sample before accepting the result |
| 17 | Define/Prepare | Practice searching one recurring event across years |
| 18 | Define/Prepare | Explain the purpose to the affected employees and confirm understanding in plain language |
| 19 | Define/Prepare | Create forecast, actual, variance, cause, and lesson fields |
| 20 | Define/Prepare | Observe the process without taking over; record where additional instruction is needed |
| 21 | Train/Practice | Define authorized later-edit and audit-note rules |
| 22 | Train/Practice | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 23 | Train/Practice | Use the record to prepare the next seven-day labor forecast |
| 24 | Train/Practice | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 25 | Train/Practice | Observe the pilot without rescuing every difficulty |
| 26 | Train/Practice | Review the completed step with the plan owner; clarify questions and document what was learned |
| 27 | Train/Practice | Revise the standard only when evidence supports the change |
| 28 | Train/Practice | Repeat the step on a second representative shift or sample before accepting the result |
| 29 | Train/Practice | Confirm every affected employee received training |
| 30 | Train/Practice | Explain the purpose to the affected employees and confirm understanding in plain language |
| 31 | Guided Execution | Complete the record every day |
| 32 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 33 | Guided Execution | Review forecast error and bias at least twice |
| 34 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 35 | Guided Execution | Add late-discovered factors with an edit reason |
| 36 | Guided Execution | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 37 | Guided Execution | Compare one event with last year’s weekday, weather, and sales |
| 38 | Guided Execution | Review the completed step with the plan owner; clarify questions and document what was learned |
| 39 | Guided Execution | Translate findings into labor and prep adjustments |
| 40 | Guided Execution | Repeat the step on a second representative shift or sample before accepting the result |
| 41 | Guided Execution | Hold a ten-minute mid-plan review with assigned owners |
| 42 | Guided Execution | Explain the purpose to the affected employees and confirm understanding in plain language |
| 43 | Guided Execution | Document exceptions, causes, and corrective actions |
| 44 | Guided Execution | Observe the process without taking over; record where additional instruction is needed |
| 45 | Guided Execution | Recheck the highest-risk handoff |
| 46 | Guided Execution | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 47 | Stress-Test | Audit completeness and tag consistency |
| 48 | Stress-Test | Check the result against safety, quality, hospitality, fairness, and workload boundaries |
| 49 | Stress-Test | Review the strongest and weakest forecast days |
| 50 | Stress-Test | Review the completed step with the plan owner; clarify questions and document what was learned |
| 51 | Stress-Test | Confirm search works for festivals, car shows, parades, school dates, and weather |
| 52 | Stress-Test | Repeat the step on a second representative shift or sample before accepting the result |
| 53 | Stress-Test | Publish the first monthly intelligence summary |
| 54 | Stress-Test | Explain the purpose to the affected employees and confirm understanding in plain language |
| 55 | Verify/Hold | Lock daily entry, weekly review, and monthly pattern analysis |
| 56 | Verify/Hold | Observe the process without taking over; record where additional instruction is needed |
| 57 | Verify/Hold | Obtain employee feedback on usability |
| 58 | Verify/Hold | Coach one identified gap, allow another attempt, and document the evidence of improvement |
| 59 | Verify/Hold | Assign the ongoing report owner |
| 60 | Verify/Hold | Check the result against safety, quality, hospitality, fairness, and workload boundaries |

# Weekly Review Record

| Review | Result | Primary Cause | Decision / Owner | Due |
| --- | --- | --- | --- | --- |
| Day 10 |  |  |  |  |
| Day 20 |  |  |  |  |
| Day 30 |  |  |  |  |
| Day 40 |  |  |  |  |
| Day 50 |  |  |  |  |
| Day 60 |  |  |  |  |

# Day-60 Verification

Was the baseline measured consistently?  ☐ Yes  ☐ No

Was the standard trained and observed?  ☐ Yes  ☐ No

Did the primary metric improve?  ☐ Yes  ☐ No

Were safety, quality, hospitality, and fairness protected?  ☐ Yes  ☐ No

Decision:  ☐ Standardize  ☐ Extend controlled test  ☐ Redesign  ☐ Stop

Sustainment rule: Complete the record daily, review comparable history weekly, and update recurring-event intelligence after every occurrence.

Manager verification: ____________________   Date: __________   Next review: __________

# Expansion Roadmap

After the Priority 12 library is installed and the book catalog is completed, the remaining improvement areas can be developed into the next controlled release. Preserve the same baseline–standard–training–execution–verification architecture so future plans remain compatible.

Guest flow: wait-list accuracy, seating efficiency, food-running, payment, resets, and takeout readiness

Guest retention: recognition, repeat visits, reactivation, reviews, reservations, and special occasions

Sales: appetizers, beverages, desserts, add-ons, promotions, events, catering, and slow periods

Labor: schedule accuracy, opening/closing productivity, breaks, overtime, cross-training, attendance, and retention

Kitchen: prep, recipes, portions, presentation, modifications, temperature, batch cooking, and availability

Inventory: receiving, storage, rotation, pars, ordering, yields, recipe costs, prices, and transfers

Front of house: section readiness, checkout, side work, refills, pre-bussing, running, expo, and handoffs

Leadership: onboarding, trainer consistency, manager readiness, coaching, recognition, accountability, and alignment

Safety and facility: restrooms, cleaning, dish flow, inspections, allergens, maintenance, injury prevention, and emergencies

Financial control: discounts, voids, cash, deposits, menu profitability, weekly review, and corrective-action closure

# Release-control note

A plan is not complete because sixty days passed. It is complete when the measurement is trustworthy, the operating standard is usable, the people were trained, the result was verified, and ownership for continued review is documented.