## Slide 1
THE GRAVITY RESTAURANT LEADERSHIP SYSTEM
The Gravity Implementation
& Verification System
How to install The Standard, prove adoption, close gaps, and protect progress
GRV-IV01–GRV-IV30
THE GRAVITY SYSTEM
Notes: Introduce GRV-IV as the controlled method for turning an approved goal and standard into verified, sustained practice.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 2
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
02
A written standard is not an installed system
A policy can be approved, distributed, and still fail in daily work.
Availability
People can find the correct version.
Adoption
People understand and use it.
Effectiveness
The intended result is demonstrated.
GRV-IV connects intent to evidence through ownership, controls, training, rollout, verification, correction, and renewal.
Notes: Distinguish publication from installation. The system requires both adoption and outcome evidence.
[Sources]
- Internal: Gravity Implementation & Verification System, Sections 1–3.
- https://www.cdc.gov/evaluation/php/evaluation-framework/index.html

## Slide 3
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
03
The Standard moves through seven steps
1
Name the Goal
Define outcome and scope
2
Face the Gap
Examine evidence and constraints
3
Set the Standard
Approve criteria and evidence
4
Build the System
Configure controls and ownership
5
Train the People
Build demonstrated competence
6
Work the Standard
Launch and verify adoption
7
Protect the Progress
Audit, certify, sustain, renew
Notes: Use this goal path as the required sequence. A later step cannot repair an undefined goal or uncontrolled standard.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 4
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
04
GRV-IV verifies implementation—it does not own every subject
GRV-IV owns
Plan, rollout, evidence, adoption verification, audit, corrective action, readiness gates, sustainment
Owning system controls
Subject definitions, operating standards, required records, approvals, and permanent controls
Qualified reviewers retain
Law, safety, food code, labor, accessibility, privacy, accounting, security, and regulated decisions
GRV-IV28 means
Internal readiness only—not certification, legal opinion, permit, assurance, or third-party attestation
Notes: Keep GRV-IV within its control boundary and route specialized judgments to qualified owners.
[Sources]
- Internal: Gravity Implementation & Verification System, boundary statement.
- https://www.eeoc.gov/laws/guidance/enforcement-guidance-retaliation-and-related-issues
- https://www.osha.gov/safety-management/worker-participation

## Slide 5
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
05
Thirty tools follow the same goal path
ONE CONTROLLED LANGUAGE
GRV-IV01 through GRV-IV30
•
Stable tool ID and official purpose
•
Named owner and approval state
•
Evidence source, date, and limitation
•
Decision, due date, verifier, and next review
•
No uncontrolled local duplicates
Notes: The Tool Index is the controlled directory linking forms, workbook records, review decisions, and evidence.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 6
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
06
1. Name the Goal before choosing activity
•
State the condition that must change
•
Name the decision owner and stakeholders
•
Define scope, exclusions, and dependencies
•
Approve measures before work begins
Notes: Start with IV01–IV04. Activity is not success; the goal, scope, owner, and measures must be explicit.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 7
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
07
2. Face the Gap with evidence—not assumption
FOUR CONTROLLED QUESTIONS
What is happening?
Use current evidence and state its limits.
Why is it happening?
Separate cause, symptom, and constraint.
What could block change?
Assess risk, capacity, readiness, and resistance.
What moves first?
Sequence by impact, dependency, and exposure.
Notes: Use IV05–IV08 to replace intuition with a bounded current-state analysis and an approved sequence.
[Sources]
- Internal: GRV-IV05–GRV-IV08.
- https://www.gao.gov/greenbook

## Slide 8
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
08
3. Set The Standard so everyone interprets it alike
•
Define observable acceptance criteria
•
Cite the controlling source and version
•
Specify evidence and sampling
•
Control approval, exceptions, and changes
•
Mark unknown or disputed evidence
If five roles can interpret it five ways, The Standard is not ready to install.
Notes: Use IV09–IV12 to make the standard observable, traceable, measurable, and controlled.
[Sources]
- Internal: GRV-IV09–GRV-IV12.
- https://www.iso.org/standard/62085.html

## Slide 9
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
09
4. Build controls before launch
Process
Define the work sequence and handoffs
Control
Prevent, detect, correct, and escalate
Owner
Assign authority, capacity, and backup
Record
Configure forms, IDs, retention, and access
Notes: IV13–IV16 convert a standard into an operable process with controls, ownership, resources, and records.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 10
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
10
Pilot at bounded scale before rollout
A PILOT MUST ANSWER
•
Who and where are included?
•
What is the success threshold?
•
What safety or rollback trigger applies?
•
Who may approve expansion?
•
What evidence will be retained?
No pilot proceeds with an unresolved stop condition.
Notes: IV17 is a controlled gate. Pilot scope, entry criteria, exit criteria, rollback triggers, and approver must be recorded.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 11
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
11
5. Train for demonstrated competence—not attendance
•
Train by role and decision authority
•
Prepare and verify the trainer
•
Require practice or demonstration
•
Record gaps, support, and reassessment
•
Protect concerns and escalation routes
Completion says a session occurred. Competence says the person can work The Standard.
Notes: IV18–IV21 connect communication and learning to observed competence, reinforcement, and adoption support.
[Sources]
- Internal: GRV-IV18–GRV-IV21.
- https://www.osha.gov/safety-management/worker-participation

## Slide 12
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
12
6. Roll out in controlled waves
Entry
Approved standard, trained roles, controls ready
Wave
Named population, timing, owner, and support
Exit
Thresholds achieved and evidence reviewed
Rollback
Trigger, authority, containment, communication
Notes: IV22 establishes controlled waves. Each wave has entry, exit, support, escalation, and rollback conditions.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 13
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
13
Verify adoption across six conditions
1
Available
2
Understood
3
Used
4
Recorded
5
Supported
6
Produces result
Adoption is not a single yes/no judgment. Record the sample, evidence, limitations, and follow-up.
Notes: IV24 requires a bounded adoption decision supported by sample and evidence rather than visibility or anecdote.
[Sources]
- Internal: GRV-IV24 Adoption Verification.
- https://www.cdc.gov/mmwr/volumes/73/rr/rr7306a1.htm

## Slide 14
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
14
Corrective action closes only after effectiveness
1
Contain exposure
2
Identify cause
3
Assign correction
4
Verify completion
5
Test effectiveness
Closing a task is not the same as removing the cause.
Notes: IV25 separates containment, correction, completion verification, and effectiveness verification.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 15
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
15
Audit criteria, sample, evidence, limitation, follow-up
•
Use defined criteria and competent reviewers
•
Choose and document a defensible sample
•
Distinguish fact, inference, and limitation
•
Protect independence and worker participation
•
Assign follow-up and verify closure
Notes: IV26 is an internal evidence review. It requires criteria, sample, evidence, limitation, finding, owner, and follow-up.
[Sources]
- Internal: GRV-IV26 Internal Audit & Evidence Review.
- https://www.iso.org/standard/19011
- https://www.gao.gov/greenbook

## Slide 16
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
16
Internal readiness certification has a strict boundary
•
Confirm required gates and unresolved conditions
•
Name the evidence and reviewer
•
Record limitations and expiration
•
Choose ready, conditional, or not ready
•
Never represent internal sign-off as external approval
Notes: IV28 is management's internal readiness decision. It does not create regulatory, legal, financial, or third-party certification.
[Sources]
- Internal: GRV-IV28 certification boundary.
- https://www.fda.gov/food/fda-food-code/food-code-2022

## Slide 17
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
17
7. Protect progress through sustainment and renewal
Monitor
Measures, drift signals, review dates
Maintain
Owners, capacity, support, records
Improve
Controlled changes and tested experiments
Renew
Annual decision and 180-day roadmap
Notes: IV29 and IV30 keep the installed system active. Renewal confirms continued relevance, ownership, controls, and next priorities.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 18
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
18
The workbook turns rollout into live control
Use yellow cells for controlled inputs
Formula columns derive status
Review exceptions before averages
Do not rename sheets or overwrite formulas
Notes: The workbook is the active control center. It joins the 30 tools, dates, owners, evidence, exceptions, checks, and decisions.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 19
IMPLEMENTATION & VERIFICATION SYSTEM
THE GRAVITY SYSTEM
19
Weekly review and checks protect progress
•
Review overdue, blocked, and failed conditions
•
Confirm evidence and limitations
•
Decide: continue, change, stop, escalate, or expand
•
Assign owner, due date, verifier, and next review
Notes: A new workbook intentionally fails three checks until approved goals, controlled standards, and evidence plans exist. Blank is not green.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.

## Slide 20
FIRST CONTROLLED MOVE
Start with three records
GRV-IV01
Name the goal and outcome
GRV-IV09
Define The Standard and acceptance criteria
GRV-IV11
Approve evidence, measurement, and sampling
Then run GRV-IV23, clear the installation checks, and verify adoption before declaring success.
THE GRAVITY SYSTEM
Notes: Close with a concrete installation sequence: goal, standard, evidence plan, and recurring implementation control.
[Sources]
- Internal: The Gravity Implementation & Verification System manual, forms, and digital control workbook.