## Dashboard
THE GRAVITY IMPLEMENTATION & VERIFICATION DASHBOARD
Release 1.2 ¦ Goal, gap, standard, build, training, operation, verification, correction, certification, renewal
| APPROVED GOALS |  |  | CONTROLLED STANDARDS | APPROVED EVIDENCE PLANS | PILOTS READY
| COMPETENCY READY |  |  | ROLLOUT WAVES READY | AVERAGE ADOPTION | OPEN CORRECTIVE ACTIONS
| OVERDUE ACTIONS |  |  | OPEN AUDIT FINDINGS | INTERNALLY CERTIFIED | FAILED CONTROL CHECKS
MANAGEMENT SIGNAL
Blank is not green. Clear the installation checks in order: approved goal, controlled standard, approved evidence plan. Then use the seven-step goal path, the weekly review, corrective-action effectiveness, and the internal readiness gate to choose the next controlled move.
| Goal Step | Ready Records | Control | Exceptions
| Name the Goal |  | Checks
| Face the Gap |  | Corrective actions
| Set the Standard |  | Audit findings
| Build the System |  | Actions
Train the People
Work the Standard
Protect the Progress
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Dashboard summarizes bounded source ranges. Clear Checks before relying on a green management signal.

## Start Here
START HERE
Use this workbook as the live control for one or more approved Gravity implementations
OPEN LINKED GRAVITY GLOSSARY →
SEVEN-STEP USE
1 | Name the Goal | Complete IV01-IV04; approve outcome, scope, owner, dependencies, measures.
2 | 1.2 | Complete IV05-IV08; establish evidence, cause, barriers, readiness, priority sequence.
3 | Set the Standard | Complete IV09-IV12; control criteria, source, version, evidence, exceptions, and change.
4 | Build the System | Complete IV13-IV17; map controls, assign owners, confirm resources, configure records, pilot.
5 | Train the People | Complete IV18-IV21; prepare roles and trainers, demonstrate competency, activate support.
6 | Work the Standard | Complete IV22-IV25; roll out in waves, run implementation review, verify adoption, correct issues.
7 | Protect the Progress | Complete IV26-IV30; audit, verify outcomes, sign readiness, sustain, renew.
WEEKLY | Operate | Review Dashboard, Implementation Review, Corrective Actions, Action Log, and Checks.
BOUNDARY | Internal readiness | GRV-IV does not create legal, regulatory, ISO, financial, employment, food-safety, or third-party certification.

## Tool Index
GRV-IV TOOL INDEX
Thirty tools across the seven-step Gravity goal path
OPEN LINKED GRAVITY GLOSSARY →
Tool ID | Goal Step | Tool Name | Owner | Frequency
GRV-IV01 | Name the Goal | Goal & Outcome Charter | Executive Sponsor | Per implementation
GRV-IV02 | 1.2 | Stakeholder & Decision Owner Map | Implementation Lead | Per implementation; update on change
GRV-IV03 | Name the Goal | Scope, Boundary & Dependency Record | Implementation Lead | At charter; on change
GRV-IV04 | Name the Goal | Implementation Case & Success Measures | Sponsor/Finance Owner | At approval; quarterly
GRV-IV05 | Face the Gap | Current-State Evidence Review | System Owner | At baseline; major review
GRV-IV06 | Face the Gap | Gap, Cause & Constraint Analysis | Implementation Lead | Per material gap
GRV-IV07 | Face the Gap | Risk, Barrier & Readiness Assessment | Risk/System Owner | Before design and launch
GRV-IV08 | Face the Gap | Priority & Sequencing Decision | Sponsor/Implementation Lead | At planning; on material change
GRV-IV09 | Set the Standard | Standard Definition & Acceptance Criteria | System Owner | Before build; on revision
GRV-IV10 | Set the Standard | Source Authority & Version Control Record | Standards Owner | Per controlled standard
GRV-IV11 | Set the Standard | Evidence, Measurement & Sampling Plan | Verification Lead | Before pilot; on measure change
GRV-IV12 | Set the Standard | Approval, Exception & Change-Control Plan | Change Authority | Before launch; per change
GRV-IV13 | Build the System | Process & Control Design Map | Process Owner | During design; annual
GRV-IV14 | Build the System | Ownership, RACI & Escalation Matrix | Implementation Lead | Before pilot; on role change
GRV-IV15 | Build the System | Resource, Capacity & Budget Readiness | Sponsor/Resource Owners | Before pilot and launch
GRV-IV16 | Build the System | Tool, Form & Record Configuration | System/Records Owner | Before pilot; on change
GRV-IV17 | Build the System | Pilot & Prelaunch Readiness Review | Sponsor/Verification Lead | Before launch
GRV-IV18 | Train the People | Role-Based Learning & Communication Plan | Training/Communication Owner | Before rollout; on change
GRV-IV19 | Train the People | Trainer Readiness & Delivery Control | Training Owner | Before each delivery cycle
GRV-IV20 | Train the People | Practice, Demonstration & Competency Record | Trainer/System Owner | Per required competency
GRV-IV21 | Train the People | Support, Reinforcement & Adoption Plan | Manager/System Owner | At rollout; weekly until stable
GRV-IV22 | Work the Standard | Launch & Controlled Rollout Plan | Implementation Lead | Per rollout
GRV-IV23 | Work the Standard | Daily/Weekly Implementation Control | System Owner | Daily/weekly during rollout
GRV-IV24 | Work the Standard | Observation & Adoption Verification | Verification Lead | Per sample plan
GRV-IV25 | Work the Standard | Issue, Exception & Corrective Action Record | System Owner | Per issue or exception
GRV-IV26 | Protect the Progress | Internal Audit & Evidence Review | Audit/Verification Lead | Quarterly/annual; risk-based
GRV-IV27 | Protect the Progress | Effectiveness & Outcome Verification | Sponsor/System Owner | At milestone; quarterly
GRV-IV28 | Protect the Progress | Readiness Certification & Management Sign-Off | Executive Sponsor | At gate; annual renewal
GRV-IV29 | Protect the Progress | Sustainment, Review & Improvement Plan | System Owner | At handoff; quarterly
GRV-IV30 | Protect the Progress | Annual System Renewal & 180-Day Roadmap | Executive Sponsor | Annual

## Gravity Glossary
LINKED GRAVITY GLOSSARY
Controlled definitions for this system. Select a term from Start Here to open this reference.
Glossary ID | Term | Gravity definition | Primary system use
GLOSS-001 | Accountable owner | The person ultimately responsible for ensuring that a required result is achieved. Work may be assigned to others, but accountability remains with this person. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-002 | Action owner | The person assigned to complete a specific action, provide the required evidence, and report its status by the due date. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-003 | Adoption | Consistent use of an approved standard, process, or tool by the people and locations expected to use it. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-004 | 1.2 | YES responses across available, understood, used, recorded, supported, and result achieved divided by six. | Implementation & Verification
GLOSS-005 | Approval | A documented decision by a person with the authority to accept, reject, release, or change a defined item. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-006 | Approved version | The currently authorized form, standard, process, workbook, or document identified through version control. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-007 | Archive | A protected location for superseded or inactive records that must be retained but must not be mistaken for the current version. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-009 | Authority | The legitimate right to make, approve, stop, escalate, or change a decision within defined limits. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-012 | Baseline | The documented starting condition used to compare later performance, adoption, risk, or results. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-018 | Closeout | The documented decision that an action, issue, incident, or implementation is complete, including evidence, verification, date, and remaining follow-up. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-020 | Competency | Demonstrated ability to perform a defined task or make a defined decision to the required standard under appropriate conditions. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-022 | Control | A designed action, rule, approval, check, restriction, or record intended to prevent, detect, correct, or contain an unacceptable result. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-026 | Corrective action | A documented response intended to eliminate, reduce, or control the cause of a confirmed problem, with an owner, due date, evidence, and effectiveness review. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-027 | Corrective action complete | Correction and effectiveness evidence are recorded with verification and close date. | Implementation & Verification
GLOSS-029 | Decision rights | The defined boundaries identifying who may decide, approve, recommend, perform, stop, or escalate a matter. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-031 | Dependency | A person, supplier, utility, system, facility, record, or resource required for an activity to operate successfully. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-033 | Due date | The approved date by which an assigned action or decision must be completed or escalated. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-034 | Escalation | A controlled transfer of a decision or issue to a person with greater authority, expertise, or responsibility because a threshold, deadline, risk, or boundary has been reached. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-036 | Evidence | Reliable information showing what occurred, what was decided, whether a requirement was met, or whether a result was achieved. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-038 | Exception | An approved, limited, and time-bound departure from a standard, supported by authority, rationale, compensating controls, and review. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-041 | Failed check | Missing, incomplete, expired, overdue, or exception evidence requiring review. | Implementation & Verification
GLOSS-043 | Frequency | The required completion rhythm for a control or tool, such as per event, daily, weekly, monthly, quarterly, annually, or when a defined change occurs. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-044 | Goal | A defined result the restaurant intends to achieve, supported by scope, ownership, measures, timing, and acceptance criteria. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-045 | Gravity standard | An approved Gravity requirement or operating expectation that remains subordinate to applicable law, regulation, official authority, contract, and platform rules. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-047 | Implementation | The controlled process of turning an approved goal or standard into configured tools, trained behavior, operating practice, evidence, verification, and sustainment. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-051 | Internal audit | A structured review of selected evidence and controls performed to determine whether an approved requirement is being followed and supported. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-052 | Internal certification | Management sign-off for a defined scope and period against GRV-IV criteria. | Implementation & Verification
GLOSS-057 | Material change | A change significant enough to affect authority, risk, results, people, guests, systems, records, training, contracts, or operating controls. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-072 | Pilot | A limited, controlled test used to identify defects, resource needs, training gaps, and evidence before wider rollout. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-075 | Qualified review | Review by a person with the required professional knowledge, organizational authority, license, certification, or subject-matter responsibility. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-078 | Ready record | Required fields and approval/evidence conditions for that register are complete. | Implementation & Verification
GLOSS-080 | Record | Retained information documenting an input, action, decision, approval, exception, result, or verification. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-081 | Recovery | The controlled restoration of operations, technology, records, facilities, finances, staffing, or other capabilities after disruption. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-086 | Review cadence | The approved schedule for examining a record, source, control, result, or standard and deciding whether action is required. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-092 | Scope | The defined locations, roles, activities, records, time period, systems, and exclusions covered by a decision or implementation. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-095 | Standard | An approved requirement or expectation used to guide work and evaluate conformance. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-097 | System owner | The person accountable for the integrity, current version, controls, evidence, performance, and renewal of a defined system. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-100 | Trigger | A defined event, condition, threshold, date, or signal that requires a tool, review, decision, action, or escalation. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-101 | Unknown | Evidence is not known or available; it is not zero, no, or not applicable. | Implementation & Verification
GLOSS-103 | Verification | A fact-based check confirming that a required action occurred and met the defined acceptance criteria. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center
GLOSS-104 | Version control | The method used to identify, approve, release, replace, archive, and trace changes to controlled materials. | Growth & Sales Building, Guest Relationship & Retention, Implementation & Verification, Manager Development, Restaurant Performance & Profitability, Risk & Continuity, Standards & Intelligence Center

## Settings
SETTINGS & CONTROLLED DEFINITIONS
Approve goals, owners, system boundaries, decision language, and evidence states before reliance
IMPLEMENTATION SETTINGS | [5 empty] | APPROVED STATE LISTS
Setting | Value | Owner | Source/Authority | Review | Notes | Readiness | Evidence | Risk | Decision
Workbook version | 1.2 | System Owner | Approved master | Annual | Do not rename sheets or formula columns | NOT STARTED | NOT COLLECTED | LOW | PROCEED
Default implementation review | Weekly | Implementation Lead | GRV-IV23 | Quarterly | Increase frequency during launch | IN PROGRESS | COLLECTED - UNVERIFIED | MODERATE | PROCEED WITH CONDITIONS
Default audit frequency | Quarterly | Verification Lead | GRV-IV26 | Annual | Risk-based | READY WITH CONDITIONS | VERIFIED - LIMITED | HIGH | REVISE
Default certification period | 12 months | Executive Sponsor | GRV-IV28 | Annual | Internal readiness only | READY | VERIFIED - SUFFICIENT | CRITICAL | RETEST
Goal ID pattern | GOAL-YYYY-NNN | Implementation Lead | GRV-IV01 | Annual | Controlled identifier | COMPLETE | SUPERSEDED |  | PAUSE
Evidence sufficiency | Decision-specific | Verification Lead | GRV-IV11 | Per plan | Record limitations | PAUSED | RESTRICTED REVIEW |  | STOP
Unknown state | UNKNOWN | System Owner | Approved definition | Annual | Never convert unknown to zero | STOPPED |  |  | ESCALATE
CERTIFY
RENEW

## Goals Scope
GOAL, OUTCOME, SCOPE & DEPENDENCIES
GRV-IV01 and IV03 ¦ Define the result before implementation activity
Goal ID | System | Outcome | Sponsor | Implementation Lead | Scope | Exclusions | Dependencies | Baseline | Target | Due Date | Approval | Record Status

## Stakeholders
STAKEHOLDER, OWNER & DECISION AUTHORITY MAP
GRV-IV02 ¦ Make ownership and voice routes visible
Map ID | Goal ID | Role/Group | Impact | Voice Route | Accountable Owner | Decision Right | Qualified Reviewer | Backup Owner | Communication Need | Unresolved Authority | Owner | Due Date | Authority State

## Success Measures
IMPLEMENTATION CASE & SUCCESS MEASURES
GRV-IV04 ¦ Connect value, process, burden, and safeguards
Case ID | Goal ID | Operational Need | Baseline | Outcome Measure | Target | Process Measure | Balancing Measure | Cost/Resource | Safeguard | Source | Frequency | Owner | Measure State

## Current State Gaps
CURRENT STATE, GAP, CAUSE & CONSTRAINT
GRV-IV05 and IV06 ¦ Separate documented, stated, observed, and unknown
Analysis ID | Goal ID | Desired State | Observed State | Gap | Impact | Evidence Source | Evidence State | People Cause | Process Cause | Capacity Constraint | Handoff | Verified Cause | Owner | Due Date | Gap State

## Risk Readiness
RISK, BARRIER & READINESS ASSESSMENT
GRV-IV07 ¦ Preserve dissent and control material barriers before launch
Assessment ID | Goal ID | Scope | Barrier | Risk Level | People Impact | Capacity | Dependency | Dissent/Concern | Mitigation | Owner | Due Date | Qualified Review | Readiness Decision | Record State

## Priorities
PRIORITY & SEQUENCING DECISIONS
GRV-IV08 ¦ Use impact, urgency, dependency, effort, risk, and reversibility
Decision ID | Goal ID | Candidate Gap | Impact 1-5 | Urgency 1-5 | Dependency 1-5 | Effort 1-5 | Risk 1-5 | Reversibility 1-5 | Priority Score | Sequence | Selected | Reason | Owner | Review Date

## Standards Versions
THE STANDARD, ACCEPTANCE CRITERIA & VERSION CONTROL
GRV-IV09 and IV10 ¦ One controlling source and one current standard
Standard ID | Goal ID | Purpose | Owner | Applies To | Required Action | Acceptance Criteria | Tolerance | Evidence | Exception Route | Controlling Source | Issuing Authority | Version | Effective Date | Approval | Control State

## Evidence Sampling
EVIDENCE, MEASUREMENT & SAMPLING PLAN
GRV-IV11 ¦ Define credible evidence before collection
Plan ID | Goal/Standard ID | Measure | Definition | Decision Use | Source | Collection Method | Population | Sample Rule | Frequency | Protection/Retention | Collector | Verifier | Threshold | Approval | Plan State

## Changes Exceptions
APPROVAL, EXCEPTION & CHANGE CONTROL
GRV-IV12 ¦ Time-limit exceptions and re-verify material changes
Change ID | Goal/Standard ID | Type | Description | Authority | Approvals | Owner | Start Date | Expiration/Due | Safeguard | Affected Records | Communication | Re-verification | Status | Timing State
Formulas:
Timing State = IF([Change ID]="","",IF(AND([Status]<>"CLOSED",[Expiration/Due]<TODAY()),"OVERDUE",IF(OR([Authority]="",[Approvals]=""),"GAP","READY")))

## Process Controls
PROCESS & CONTROL DESIGN MAP
GRV-IV13 ¦ Make inputs, control points, evidence, and failure modes explicit
Map ID | Goal ID | Trigger | Input | Step | Owner | Control Point | Output | Evidence | Failure Mode | Prevention | Detection | Escalation | Feedback Measure | Control State

## Ownership RACI
OWNERSHIP, RACI & ESCALATION MATRIX
GRV-IV14 ¦ Every permanent control needs permanent accountable ownership
Matrix ID | Work/Decision | Accountable | Responsible | Consulted | Informed | Backup | Decision Right | Escalation Trigger | Response Time | Conflict | Resolution | Approval | Review Date | Coverage State

## Resource Readiness
RESOURCE, CAPACITY & BUDGET READINESS
GRV-IV15 ¦ Verify the means to operate before launch
Review ID | Goal ID | Resource Type | Requirement | Available | Gap | Capacity Limit | Contingency | Owner | Required Date | Status | Evidence | Decision | Readiness State

## Configuration
TOOL, FORM & RECORD CONFIGURATION
GRV-IV16 ¦ Control fields, IDs, access, retention, workflow, and versions
Config ID | Goal ID | Tool/Form | Owner | Version | Workflow | Required Fields | Record ID Rule | Access | Retention | Integration | Conflicting Drafts Removed | Test Result | Approval | Release State

## Pilot Readiness
PILOT & PRELAUNCH READINESS
GRV-IV17 ¦ Bounded test, evidence, correction, and gate decision
Pilot ID | Goal ID | Scope | Owner | Start Date | End Date | Entry Criteria | Standard Tested | Sample | Result | Adoption | Risk/Incident | Limitations | Correction | Retest | Gate Decision | Gate State

## Learning Plan
ROLE-BASED LEARNING & COMMUNICATION PLAN
GRV-IV18 ¦ Define what each role must know, do, practice, and retain
Plan ID | Goal ID | Role/Group | Required Outcome | Prior Knowledge | Access Need | Know | Do | Practice | Job Aid | Question Route | Communication | Owner | Delivery Date | Release Condition | Plan State

## Trainer Competency
TRAINER READINESS, DELIVERY & COMPETENCY
GRV-IV19 and IV20 ¦ Practice and demonstration—not attendance alone
Record ID | Goal ID | Trainer/Person ID | Role | Content/Standard Version | Authority Verified | Delivery/Practice Date | Scenario/Work | Observed Action | Result | Feedback | Support | Limitations | Verifier | Competency State | Decision Ready

## Support Adoption
SUPPORT, REINFORCEMENT & ADOPTION PLAN
GRV-IV21 ¦ Build listening and targeted recovery after training
Plan ID | Goal ID | Role/Group | Owner | Period | Adoption Target | Job Aid | Coaching | Help Route | Reminder | Listening Route | Recognition | Adoption Signal | Barrier | Recovery Action | Due Date | Plan State

## Rollout
LAUNCH & CONTROLLED ROLLOUT PLAN
GRV-IV22 ¦ Wave entry criteria, support, rollback, and go/no-go
Plan ID | Goal ID | Wave/Scope | Owner | Launch Date | Entry Criteria | Communication | Data/Record Change | Support | Risk | Rollback Trigger | Exit Criteria | Open Condition | Go/No-Go | Approved By | Wave State

## Implementation Review
DAILY/WEEKLY IMPLEMENTATION CONTROL
GRV-IV23 ¦ Review exceptions and decisions—not activity theater
Review ID | Goal ID | Date/Period | Chair | Scope | Data Through | Adoption | Exceptions | Risk | Support Demand | Overdue Actions | Evidence Gap | Decision | Owner | Due Date | Verification | Review State
Formulas:
Review State = IF([Review ID]="","",IF(OR([Data Through]="",[Decision]="",[Owner]=""),"GAP",IF(AND([Due Date]<TODAY(),[Verification]=""),"OVERDUE","READY")))

## Adoption Verification
OBSERVATION & ADOPTION VERIFICATION
GRV-IV24 ¦ Test availability, understanding, use, records, support, and results
Verification ID | Goal ID | Standard ID | Location/Role | Observer | Date | Available | Understood | Used | Recorded | Supported | Result Achieved | Evidence | Limitations | Correction | Next Sample | Adoption Score | State
Note on Q6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The score is a decision aid. Review sample quality, limitations, and risk before concluding that adoption is sufficient.

## Corrective Actions
ISSUE, EXCEPTION & CORRECTIVE ACTION
GRV-IV25 ¦ Close only after effectiveness is verified
Record ID | Goal ID | Issue/Exception | Date | Source | Risk | Containment | Cause Review | Correction | Owner | Due Date | Escalation | Evidence | Effectiveness Check | Residual Risk | Verified By | Close Date | Action State
Formulas:
Action State = IF([Record ID]="","",IF([Close Date]<>"","COMPLETE",IF([Due Date]<TODAY(),"OVERDUE",IF(OR([Containment]="",[Correction]="",[Owner]=""),"GAP","IN PROGRESS"))))

## Audit Evidence
INTERNAL AUDIT & EVIDENCE REVIEW
GRV-IV26 ¦ Criteria, sample, competent review, findings, limitations, follow-up
Audit ID | Goal/System | Scope | Criteria | Auditor/Reviewer | Start Date | End Date | Sample | Methods | Evidence State | Finding | Severity | Limitations | Corrective Action | Owner | Due Date | Follow-Up | Finding State
Formulas:
Finding State = IF([Audit ID]="","",IF([Finding]="","GAP",IF(AND([Corrective Action]<>"",[Follow-Up]<>""),"COMPLETE",IF([Due Date]<TODAY(),"OVERDUE","IN PROGRESS"))))

## Outcome Verification
EFFECTIVENESS & OUTCOME VERIFICATION
GRV-IV27 ¦ Verify results, balancing effects, burden, harm, and limitations
Review ID | Goal ID | Period | Owner | Baseline | Outcome Target | Outcome Result | Process Result | Balancing Result | Burden/Harm | Attribution Limits | Evidence Quality | Effective Status | Correction | Decision | Approval | Next Review | Record State

## Certification
INTERNAL READINESS CERTIFICATION & SIGN-OFF
GRV-IV28 ¦ Internal management decision for a defined scope and period
Certification ID | Goal/System | Scope | Gate | Sponsor | Decision Date | Standard Met | Ownership Active | Training Verified | Adoption Verified | Issues Controlled | Evidence Current | Status | Conditions | Expiration | Signatories | Next Review | Certification State
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is an internal management readiness state for a defined scope and period. It is not legal, regulatory, ISO, financial, employment, food-safety, or third-party certification.

## Sustainment Renewal
SUSTAINMENT, IMPROVEMENT & ANNUAL RENEWAL
GRV-IV29 and IV30 ¦ Monitor drift, improve, and renew authority
Plan/Renewal ID | Goal/System | Owner | Handoff Date | Stable-State Criteria | Monitoring | Review Cadence | Drift Trigger | Refresher | Audit Frequency | Change Control | Backlog Priority | 30-Day Milestone | 90-Day Milestone | 180-Day Outcome | Next Review | Renewal Decision | Plan State

## Action Log
IMPLEMENTATION ACTION LOG
All open conditions, corrections, support commitments, and verification actions
Action ID | Goal ID | Source Tool | Decision/Action | Owner | Due Date | Priority | Status | Evidence Required | Support | Verifier | Closed Date | Effectiveness Note | Action State
Formulas:
Action State = IF([Action ID]="","",IF(OR([Status]="CLOSED",[Status]="CANCELLED"),"COMPLETE",IF([Due Date]<TODAY(),"OVERDUE","IN PROGRESS")))

## Checks
WORKBOOK CONTROL CHECKS
Blank state intentionally fails goal, standard, and evidence-plan installation checks
Check | Exceptions | Status | Owner / Fix
No approved goal charters |  |  | Sponsor / IV01
No controlled standards |  |  | System Owner / IV09
No approved evidence plans |  |  | Verification Lead / IV11
Goal records have gaps |  |  | Implementation Lead
Stakeholder authority gaps |  |  | Implementation Lead
Current-state evidence gaps |  |  | System Owner
High risks lack mitigation |  |  | Risk/System Owner
Standard/version gaps |  |  | Standards Owner
Expired exceptions or changes |  |  | Change Authority
Control maps incomplete |  |  | Process Owner
Ownership/backup gaps |  |  | Implementation Lead
Resource readiness gaps |  |  | Resource Owners
Configuration not released |  |  | Records Owner
Pilot not decision-ready |  |  | Verification Lead
Competency records incomplete |  |  | Training/System Owner
Rollout not ready |  |  | Implementation Lead
Adoption below full standard |  |  | Verification Lead
Corrective actions overdue |  |  | System Owner
Audit findings overdue |  |  | Audit Lead
Certification not ready |  |  | Executive Sponsor
Sustainment plans incomplete |  |  | System Owner
Actions overdue |  |  | Action Owner
INTERPRETATION
A failed check identifies missing, incomplete, expired, overdue, or exception evidence. It does not by itself prove misconduct, legal noncompliance, or system failure. Protect people, inspect the controlling source, assign the qualified owner, correct the condition, verify effectiveness, and record the decision. The first three checks are expected to fail in a new workbook.

## Definitions Sources
DEFINITIONS, BOUNDARIES & OFFICIAL SOURCES
Internal readiness is decision-specific and does not replace qualified external authority
CONTROL DEFINITIONS
Term | Definition | Primary Sheet | Decision Use | Owner | Review
Ready record | 1.2 | Multiple | Gate input; not automatic certification | System Owner | Weekly
Adoption score | YES responses across available, understood, used, recorded, supported, and result achieved divided by six. | Adoption Verification | Identify recovery or verification need | Verification Lead | Per sample
Corrective action complete | Correction and effectiveness evidence are recorded with verification and close date. | Corrective Actions | Closure decision | System Owner | Weekly
Internal certification | Management sign-off for a defined scope and period against GRV-IV criteria. | Certification | Readiness gate only | Executive Sponsor | At gate/annual
Failed check | Missing, incomplete, expired, overdue, or exception evidence requiring review. | Checks | Correct or accept through authority | Owning role | Weekly
Unknown | Evidence is not known or available; it is not zero, no, or not applicable. | All | Reduce conclusion strength | Verifier | Per decision
BOUNDARIES
GRV-IV owns |  |  | Implementation planning, rollout control, adoption verification, internal audit, corrective action, readiness gates, sustainment, and renewal.
Owning systems own |  |  | Their standards, definitions, records, subject decisions, qualified approvals, and permanent operating controls.
Internal sign-off only |  |  | GRV-IV does not create an ISO certificate, regulatory approval, food-safety permit, legal opinion, financial assurance, employment decision, or third-party attestation.
People and reporting |  |  | Do not suppress concerns, dissent, safety reports, complaints, protected activity, or evidence limitations. Route them through approved channels.
Data restraint |  |  | Use controlled IDs and minimum necessary evidence; keep restricted records in authorized systems.
OFFICIAL SOURCES
ISO 9001 - Quality management systems |  |  |  | https://www.iso.org/standard/62085.html
ISO 19011 - Guidelines for auditing management systems |  |  |  | https://www.iso.org/standard/19011
U.S. GAO - 2025 Green Book |  |  |  | https://www.gao.gov/greenbook
OSHA - Safety and Health Programs |  |  |  | https://www.osha.gov/safety-management
OSHA - Program Evaluation |  |  |  | https://www.osha.gov/safety-management/program-evaluation
OSHA - Worker Participation |  |  |  | https://www.osha.gov/safety-management/worker-participation
CDC - Program Evaluation Framework, 2024 |  |  |  | https://www.cdc.gov/mmwr/volumes/73/rr/rr7306a1.htm
CDC - Evaluation Framework Action Guide |  |  |  | https://www.cdc.gov/evaluation/php/evaluation-framework/index.html
FDA - Food Code 2022 |  |  |  | https://www.fda.gov/food/fda-food-code/food-code-2022
FDA - Supplement to the 2022 Food Code |  |  |  | https://www.fda.gov/media/183271/download
NIST SP 800-53A Rev. 5 - Control Assessment |  |  |  | https://csrc.nist.gov/news/2022/security-privacy-control-assessment-procedures
EEOC - Retaliation and Related Issues |  |  |  | https://www.eeoc.gov/laws/guidance/enforcement-guidance-retaliation-and-related-issues